Chapter 33 - Financial and Budgetary Provisions

Action Plan for Establishment of European Union's Own Resources System in Montenegro

Annual Report for 2020

July, 2021

Introduction

Negotiation Chapter 33 – Financial and Budgetary Provisions include rules on own resources which represent the financial revenue of the European Union’s budget. From the first day of membership, Montenegro will pay the necessary contributions to the joint budget of the European Union, which will allow it to use a certain amount of Union expenditures from the Cohesion Fund and the Structural Funds.

At the Intergovernmental Conference in Brussels in December 2014, Montenegro opened accession negotiations in Chapter 33, and by the time of accession it is obliged to establish a coordination structure and implementing rules to ensure the correct calculation, collection, forecasting, disbursement and control of own resources and reporting to the EU on the own resources rules implementation.

At its session on July 26th, 2018, the Government of Montenegro reviewed the Information on the plan for meeting the final benchmark for temporary closing of negotiations in Chapter 33 - Financial and Budgetary Provisions and instructed the Ministry of Finance to prepare and submit to the Government in the first quarter of 2019 a revised action plans for the establishment of the European Union's own resources system in Montenegro, with defined obligations of the institutions carrying out activities to complete the measures.

At its session on April 4th, 2019, the Government of Montenegro adopted the Information on Fulfillment of Obligations Defined through Negotiating Chapter 33 - Financial and Budgetary Provisions, as well as the Revised action plan for establishing the European Union's own funds system in Montenegro with defined obligations of institution carrying out activities to complete the measures from the Action plan. With the same conclusion, the Government instructed the Ministry of Finance to report annually on the implementation of the Action Plan to the Government of Montenegro.

The Action Plan envisages activities related to establishment of general administrative conditions in the field of own resources, management of traditional own resources, management of own resources based on value added tax and management of own resources based on gross national income. According to the defined activities aiming to fulfil the measures, the obligations of the institutions carrying out activities are divided per chapters.

The Ministry of Finance (Ministry of Finance and Social Welfare), i.e., the Directorate for Tax and Customs System and the Customs Administration (Revenue and Customs Administration) are responsible for obligations to establish an information system and procedures for keeping accounts, establishing a system of reporting on traditional own resources, harmonising the system of customs debt write-off and harmonising the system of administrative cooperation in the field of tax collection and other charges.

The Tax and Customs System Directorate, Tax Administration and Statistical Office are responsible for the activities of calculating the weighted average VAT rate, positive and negative compensations, making a simulation of the report on the VAT own resources base and harmonising the Law on Value Added Tax with the acquis communautaire.

The Statistical Office is responsible for activities on harmonisation of GDP and GNI, while the Ministry, i.e., the Directorate for Tax and Customs System, is responsible for activities on harmonisation of legislation in that area with the acquis communautaire.

The implementation of activities during 2020 was focused on further capacity building in accordance with the recommendations of the European Commission Report on Montenegro in order to monitor the implemented activities and plan future activities in this area. The European Commission Report states that limited progress has been made in strengthening the administrative capacity for coordination and management of own resources, while an updated Action Plan for managing the own resources system was adopted in 2019, thus fulfilling one of the recommendations from the previous report. Therefore, the recommendations indicate that the alignment of the institutional framework and administrative rules for the own resources management system, as well as the legal framework for VAT with the acquis communautaire particularly need to be further improved. In addition, the recommendations refer to further improvement of the harmonisation of the legal basis for related areas and policies that affect the proper application of the own resources system and provision of adequate capacities in the Directorate for Coordination and Management of EU Own Resources and in all institutions included in the own resources system.

In accordance with the defined activities to fulfil measures aimed at their timely and precise fulfilment and the deadline for fulfilment of measures, the obligations of the institutions that are activities holders are divided per chapters.

Traditional Own Resources

In the area of ​​Traditional Own Resources (TOR), the Action Plan defines the objectives related to the establishment of the Information System (IS) and procedures for keeping accounts A (regular accounts) and B (separate accounts), preparation of the service for establishing a reporting system related to traditional own resources collected on the basis of detected cases of fraud and irregularities, harmonisation of the Decree on the Implementation of the Customs Law of Montenegro with the EU Regulation with special reference to the harmonisation of customs debt write-offs, as well as harmonisation of the customs law with the EU acquis.

Objective: Establishment of information system and procedures for keeping accounts A and B

In the previous period (during 2019), activities were realised related to the following:

- Study of EU regulations and requirements related to the accounting system of traditional own resources

- Analysis of the accounting rules of the system of Traditional own resources based on A and B accounts, in accordance with the experience gained from working visits to EU member states

- Defining and marking the income that will be classified in special A and B accounts, according to whether the receivables are paid, unpaid, secured, unsecured or disputed through the prepared Proposal of the Rulebook on the form, content and manner of submitting the customs declaration and other forms used in customs proceedings

- A and B account management simulation exercise

In the previous period (during 2019), activities were realised related to the following:

- Study of EU regulations and requirements related to the accounting system of traditional own resources

- Analysis of the accounting rules of the system of Traditional own resources based on A and B accounts, in accordance with the experience gained from working visits to EU member states

- Defining and marking the income that will be classified in special A and B accounts, according to whether the receivables are paid, unpaid, secured, unsecured or disputed through the prepared Proposal of the Rulebook on the form, content and manner of submitting the customs declaration and other forms used in customs proceedings

- A and B account management simulation exercise

During 2020, the Action Plan envisaged activities for the adoption of the Instruction for the application of EU's Traditional own resources in Montenegro, which would specify the sources, accounts, occurrence of receivables, deadlines for posting, recording receivables, reporting forms for the Statistical Office needs and development of specification of functional requirements to introduce the A and B account management application, reporting system and upgrade the existing application.

These activities are defined as an integral part of the Twinning Light Project - Establishing EU's Own Resources System in Montenegro, which was approved in December 2020 by the Steering Committee of the Instrument for European Integration. This project envisaged full support for the management of EU’s own resources in Montenegro, in order to establish accurate calculation, planning, payment, control and reporting of EU’s own resources in accordance with the acquis communautaire. The realisation of this project in accordance with the planned dynamics is planned in the next period, within which these activities will be realised.

Objective: Preparation of the service for the establishment of a reporting system regarding traditional own resources collected based on the results of detected cases of fraud and irregularities

In the previous period (during 2019), activities were realised relating to the following:

- Submission of a simulation of the Report with a description of detected cases of fraud and irregularities involving traditional own resources in the amount of more than €10,000.00

In the previous period (during 2019), activities were realised relating to the following:

- Submission of a simulation of the Report with a description of detected cases of fraud and irregularities involving traditional own resources in the amount of more than €10,000.00

During 2020, activities relate to:

- Preparation of report on seized goods through the OWNRES system (continuous)

- Analysis of reports with a description of detected cases of fraud and irregularities, and the gradual introduction of the obligation of the same method of reporting for the entire customs territory of Montenegro

System reporting application (OWNRES) - reporting on detected cases of irregularities and fraud is not developed within the IT system of the Administration, but data from existing databases will be entered into the OWNRES web application. When filling in the reporting form in the OWNRES web application, data from the Customs Information System (CIS), Risk Management Register (RUR) and Electronic Risk Information Register (ERRI) applications will be used. RUR and ERRI are applications developed for the purpose of collecting and recording information in the field of customs controls and risk analysis.

The instructions for use of the applications of the Risk Management Register and the electronic risk information system prescribe the mandatory entry of data on subsequent controls and seizures of goods, which ensures that information relevant to OWNRES reporting is entered into a centralised electronic database. RUR, within the part of the Report, contains a report on changes (increases) of declarations entered in the CIS, while ERRI is an electronic register of risk information, into which data on the results of customs controls, violations, criminal charges, seizures and subsequent controls is entered.

Also, during 2020, the Application for Inspection Supervision was developed, which includes a comprehensive analysis of business processes and the work of customs controls in order to provide detailed information for the establishment and use of IT solutions for the process of customs control management. The application contains a module for developing a control plan for inspection supervision, with the main purpose of creating annual control plans (or other periodic plans), as well as creating a list of economic entities selected for control based on certain criteria using the mathematical-statistical method and targeted selection method. Activities related to:

- Elaboration and determination of the procedures necessary for the preparation of the rules on the annual reporting on results to the Commission's in accordance with Article 17.5 of Council Regulation 1150/2000Preparation of reports on established obligations in subsequent controls and for which there is no customs debt insurance, which should be recorded in account B,

are defined as an integral part of the Twinning Light Project - Establishing EU's Own Resources System in Montenegro, which was approved in December 2020 by the Steering Committee of the Instrument for European Integration which provides full support for the management of EU’s own resources in Montenegro, in order to establish accurate calculation, planning, payment, control and reporting to EU on own resources in accordance with the EU acquis communautaire. The realisation of this project in accordance with the planned dynamics is planned in the next period, within which these activities will be realised.

Objective: Aligning customs legislation with the EU acquis communautaire

Regarding obligations to harmonise customs legislation with the acquis and secondary legislation, a draft of the new Customs Law was prepared, and work began on a new Decree on the Form, Content and Manner of Submitting Customs Declarations and other forms used in customs procedures, which will, among other things, define the marking of revenues and receivables, which will precisely define the classification of revenues into A and B accounts.

The Ministry of Finance and Social Welfare, in cooperation with the Revenue and Customs Administration, with the technical assistance of GIZ, prepared a draft of the new Customs Law, in order to harmonise it with the EU Customs Law. After receiving a positive opinion from the Secretariat for Legislation (end of 2020) and other competent institutions, the Draft Customs Law, with the table of harmonisation and accompanying documentation, was forwarded to the European Commission for an opinion. The new Law will improve communication between the customs service and economic entities, which will be done electronically, which will certainly contribute to greater legal certainty, simplification, modernisation and rationalisation of customs procedures in accordance with contemporary needs. For the full implementation of the new Customs Law, it is necessary to develop new and upgrade existing IT systems, which requires some time, and the application of provisions governing the use of electronic systems that are not operational will be postponed until their establishment, which is the practice in the European Union too.

Own Resources Based on Value Added Tax

Objective: Calculation of the weighted average rate of VAT and positive and negative fees and preparation of the VAT report simulation

The start of the implementation of the project Tax Administration Reform in cooperation with the World Bank worth € 18.8 million is of particular importance for the purpose of adequate calculation of EU own resources. The development goal of the project is to improve the effectivity of operational functions and reduce the costs of corporate taxpayers when complying with tax obligations. The project supports the long-term vision of Montenegro, which is the Tax Administration with modernised risk-based business processes that contribute to the efficient collection of taxes and social security contributions from all sources of economic activity. The increase in the settlement of tax liabilities will generate a larger inflow of income from which basic services for citizens will be provided. Improving the capacity of the Tax Administration will also contribute to achieving the country's goal of EU accession and economic integration with EU member states. The implementation of the project will contribute to better VAT calculation, and ultimately create preconditions for efficiency in the preparation of reports on simulation of VAT calculation, in accordance with the requirements related to the calculation of traditional own resources, which is implemented in cooperation with Statistical Office.

Within the project, the Functional Requirement Document (FRD) was prepared, and an integral part of the FRD document is the part related to VAT calculation (calculation, refund, risk analysis). Implementation of the integrated IT system will automatise all business processes, which will enable more efficient collection of all types of taxes, as well as the use of modern tools for performing tax controls, which will contribute to increasing revenues.

The introduction of an electronic fiscalisation system is envisaged from January 2021, which is planned to monitor all issued invoices. The introduction of e-fiscalisation, as an integral part of the integrated system, will enable real-time monitoring of the turnover of all economic entities (natural and legal persons). In this way, it will contribute to the reduction of tax fraud and evasion, especially in the field of ​​VAT.

One of the components of the project are the analytical processes, which include the calculation of the tax gap. With the help of an external consultant, the first estimates were made, the methodology and calculations of the tax gap for VAT, income tax, contributions and profit tax for 2017 and 2018 were defined, based on available data.

According to preliminary results, the amount of the tax gap was obtained. The methodology used was presented and referred to all data sources obtained from the competent institutions in Montenegro, but also obtained through the AMECO database, which is the annual database of macroeconomic data of the European Union.

The assessment of the tax gap for 2019 is in the process of being produced. The production process itself, which has been slowed down due to the coronavirus epidemic, is underway and a preliminary report is expected during 2021.

In addition, the concept of the tax gap and the difference between the compliance gap and the policy gap are explained. The work on the model and the calculation of the gap itself for all GDP components by the consumption method are defined. For the calculation of potential collection of these two categories of revenues, data are not available, so data and structure from countries in the region and the EU were used, as well as the Ministry's assessment, which was done through a project funded by EU resources, which is considered to be the optimal way for calculation, considering the current availability of necessary data.

In the part of the tax gap for profit tax, the methodology for calculation is defined, but in the absence of the necessary data, which would be used to calculate the potential collection, there is no evident insight into the current gap in this category. Further development will define the methodology and set a model that will provide the opportunity to calculate the tax gap for this category of income.

The harmonisation of regulations on value added tax is being done gradually. In this regard, on July 30th , 2020, the Parliament of Montenegro adopted the Law Amending Law on Value Added Tax (Official Gazette of Montenegro, No. 80/20), which, among other things, made certain changes in taxation of turnover of goods, services and imports at a reduced rate of 7%. Namely, it is prescribed that food preparation and serving services, bottled drinking water and non-alcoholic non-carbonated beverages in restaurants and facilities where catering services are provided are taxed at a reduced rate of 7%, and this legal solution will apply from September 1st , 2021. In addition, taxation at a reduced rate of 7% on services of preparation and serving of food, drinks and beverages, except alcoholic beverages, carbonated beverages with added sugar and coffee in facilities for catering services was prescribed, and this solution will apply until August 31st, 2021.

Also, the Law prescribes exemption from VAT on import, or taxation at a rate of 0% in domestic trade on provision of products or services to state authorities and organisations and authorities of local self-government units and other public bodies, when provided through a donation contract, or  delivery of medical devices and protective equipment as a donation to state authorities and organisations and authorities of  local self-government units and other public bodies, intended to curtail the consequences caused by an epidemic of an infectious disease.

The Law in question introduced a new legal solution that facilitates business transactions for the taxpayer, by giving him the opportunity to issue an invoice in electronic form with the consent of the recipient of the invoice, under conditions and in the manner prescribed by law governing this field. A novelty was introduced also that the monthly application for VAT calculation is submitted electronically only, which is in accordance with the European tax legislation, and the same tax solution started to be applied in November 2020.

Own Resources Based on Gross National Income

Objective: Reconciliation of data for Gross Domestic Product (GDP) and Gross National Income (GNI)

In the previous period (during 2019), activities were realised that relate to:

- Calculation of Gross National Income (GNI) for 2018

In the previous period (during 2019), activities were realised that relate to:

- Calculation of Gross National Income (GNI) for 2018

- Calculation of Gross National Income (GNI) for 2019

In September 2020, the Statistical Office published the GNI of Montenegro for 2019 in accordance with the ESA 2010 methodology, which indicates that the GNI time series for the period 2010-2019 is available. GNI is a measure of income based on gross domestic product data and balance of payments data.

Gross Domestic Product is calculated according to the methodology of the European system of national and regional accounts (ESA 2010). The transition from Gross Domestic Product to Gross National Income was made based on balance of payments statistics and is compiled in accordance with the methodology of the International Monetary Fund. Gross National Income is equal to Gross Domestic Product increased by the primary income that residential units receive from the rest of the world and less primary payments of income from residential units in the rest of the world. GNI data are available from 2010 to 2019 and published on the website of the Statistical Office (www.monstat.org).

With the support of IPA projects, work is underway to define sources and methods for calculating GDP according to the revenue method. Work will continue on the analysis of experimental data and the improvement of the calculation of compensation to employees.

The calculation of GDP partly includes an estimate of the non-covered economy for legal activities (underreporting) as well as illegal activities. Through continuous IPA support, work will continue on improving sources and methods for compiling GDP.

Please note that the national accounts cover the economy not included and related to the following activities: (Underreporting of entrepreneurs' income above €18,000 of income; Estimates of other activities not observed, such as tips, private lessons and paid services to household members; Estimates related to illegal activities not covered, such as drugs and prostitution).

The methodology used to estimate the illegal economy is based on the Eurostat IEA Manual (Handbook related to the compilation of statistics on illegal economic activities). NOE (Non-observed economy) estimates are included in GDP and are not presented separately.

The Statistical Office conducted a statistical survey which collected detailed data on the structure of revenues, expenditures and stocks with the technical support of the IPA 2010 national project. Work on the calculation of balanced supply and use tables continues through support funded through IPA projects. Supply and use tables provide a detailed analysis of the production and use of products and services; provides information on the sources of product supply in the economy; provides information on the sources where the products, as well as other primary factors of production are consumed. The basic principle that emerges from the two tables is that the total supply of products must correspond to the total use of those products.

Within the IPA 2014 project, the Description of Data Sources and Methods Used to Compile GDP and GNI for the reference year 2015 was prepared and submitted to Eurostat. In the coming period, work will be done on updating the GNI inventory, bearing in mind the continuous activities to improve the sources and methods for a comprehensive compilation of aggregates of Gross Domestic Product and Gross National Income. The update of the GNI Inventory will be supported through the IPA project.

Administrative Capacity

In order to establish the best possible institutional organisation and strong interagency cooperation between all institutions and authorities involved in the implementation of the own resources system, cooperation will be continuously implemented through the activities of the working group and expert support from the Twining Light Project.

In December 2020, the Twining Light Project worth €225,000.00 was approved. The aim of the project is to support Montenegro in establishing an efficient structure in coordination and establishing its own EU resources in line with the acquis communautaire and the requirements of the negotiation chapter 33. The focus of the project will be on further harmonisation of institutional framework and legislation with EU requirements, ensuring at the same time administrative capacity for own resources in Montenegro. More specifically, it will contribute to the establishment of appropriate correction mechanisms, precise rules and regulations on own resources, the collection and availability of traditional own resources, the payment of resources based on VAT and GNI, and the establishment of the coordination structure and reporting.

Improvement in this area is planned through the parallel development of three components.

- The first component relates to the development of capacities in all institutions carrying out activities for the establishment of the EU own resources system in Montenegro, which is reflected in the strengthening of administrative capacities for proper planning, coordination and calculation of own resources, as well as exchange of experiences with EU member states in the own resources field.

- The second component includes establishment of procedures and strengthening of the institutional framework, which is reflected in the establishment of account opening procedures, management procedures, procedures in developing reporting systems, as well as guidelines and methodology for calculating own resources by type.

- The third component includes the harmonisation of legislation in the field of own resources, which is reflected in the analysis of existing legislation in terms of identifying space and making recommendations for improving the legislative framework.

In accordance with the Decree on the organisation and manner of work of the state administration (Official Gazette of Montenegro No. 41/2021) Revenue and Customs Administration